## Combined_Project_Status_Report
Page/Module | API Category | Integration Status | API Endpoints | Features Fully Integrated | Features Missing/Partially Integrated | Integration % | Notes | Column1 | Column2 | Column3
Login | Auth | Fully Integrated | auth/login | User authentication | N/A | 67% | Login | token refresh working
Login | Auth | Fully Integrated | auth/refresh | Token refresh | N/A | 67% | Login | token refresh working
Login | Auth | Partially Available | auth/change-password | Change password | N/A | 67% | API exists but not in UI
Dashboard | Dahsboard | Fully Integrated | projects/dashboard | Dashboard data with KPIs | N/A | 100% | KPI cards | project list | notifications | workload all integrated
Dashboard | Dahsboard | Fully Integrated | tasks/my-tasks | My tasks list | N/A | 100% | KPI cards | project list | notifications | workload all integrated
Dashboard | Dahsboard | Fully Integrated | notifications | User notifications | N/A | 100% | KPI cards | project list | notifications | workload all integrated
Dashboard | Dahsboard | Fully Integrated | departments | Department list | N/A | 100% | KPI cards | project list | notifications | workload all integrated
Dashboard | Dahsboard | Fully Integrated | users | User list | N/A | 100% | KPI cards | project list | notifications | workload all integrated
Dahsboard | Dahsboard | Partially | AI insights | Escalations | High risk interventions | 50% | AI integrations missing
Dashboard | Projects | Fully Integrated | tasks/overdue | Overdue tasks | N/A | 100% | KPI cards | project list | notifications | workload all integrated
Projects | Projects | Fully Integrated | projects | Project list | N/A | 79% | Project CRUD complete | Basic UI compelted, needs modern ui design implementations
Projects | Projects | Fully Integrated | projects/{id} | Project details | N/A | 79% | Project CRUD complete | Basic UI compelted, needs modern ui design implementations
Projects | Projects | Fully Integrated | projects (POST) | Create project | N/A | 79% | Project CRUD complete | Basic UI compelted, needs modern ui design implementations
Projects | Projects | Fully Integrated | projects/{id} (PUT) | Update project | N/A | 79% | Project CRUD complete | Basic UI compelted, needs modern ui design implementations
Projects | Projects | Fully Integrated | projects/{id}/status (PATCH) | Update status | N/A | 79% | Project CRUD complete | Basic UI compelted, needs modern ui design implementations
Projects | Projects | Fully Integrated | projects/{id}/progress | Progress tracking | N/A | 79% | Project CRUD complete | Basic UI compelted, needs modern ui design implementations
Projects | Projects | Fully Integrated | projects/{id}/documents (POST) | Document upload | N/A | 79% | Project CRUD complete | Basic UI compelted, needs modern ui design implementations
Projects | Projects | Fully Integrated | projects/{id} (DELETE) | Delete project | N/A | 79% | Project CRUD complete | Basic UI compelted, needs modern ui design implementations
Projects | Projects | Partially Available | projects/{id}/ai/health | AI health | API exists but limited UI | 79% | Project CRUD complete | Basic UI compelted, needs modern ui design implementations
Projects | Projects | Partially Available | projects/{id}/ai/insights | AI insights | API exists but not fully used | 79% | Project CRUD complete | Basic UI compelted, needs modern ui design implementations
Projects | Projects | Partially Available | projects/{id}/ai/optimize-resources | Resource optimization | API exists but not fully used | 79% | Project CRUD complete | Basic UI compelted, needs modern ui design implementations
Milestones | Work Management | Fully Integrated | milestones/by-project/{projectId} | Milestones by project | N/A | 100% | Full CRUD for milestones | Basic UI compelted, needs modern ui design implementations
Milestones | Work Management | Fully Integrated | milestones (POST) | Create milestone | N/A | 100% | Full CRUD for milestones | Basic UI compelted, needs modern ui design implementations
Milestones | Work Management | Fully Integrated | milestones/{id} | Get milestone | N/A | 100% | Full CRUD for milestones | Basic UI compelted, needs modern ui design implementations
Milestones | Work Management | Fully Integrated | milestones/{id} (PUT) | Update milestone | N/A | 100% | Full CRUD for milestones | Basic UI compelted, needs modern ui design implementations
Milestones | Work Management | Fully Integrated | milestones/{id}/complete (PATCH) | Mark complete | N/A | 100% | Full CRUD for milestones | Basic UI compelted, needs modern ui design implementations
Milestones | Work Management | Fully Integrated | milestones/{id} (DELETE) | Delete milestone | N/A | 100% | Full CRUD for milestones | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/by-project/{projectId} | Tasks by project | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/my-tasks | My tasks | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id} | Task details | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks (POST) | Create task | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id} (PUT) | Update task | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/progress (PATCH) | Update progress | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/status (PATCH) | Update status | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/assign (POST) | Assign task | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/ai/recommend-assignee | AI assignee recommendation | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/ai/delay-prediction | AI delay prediction | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/escalate (POST) | Escalate task | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/comments (POST) | Add comment | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/attachments (POST) | Upload attachment | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/time/start (POST) | Start timer | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/time/stop (POST) | Stop timer | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id} (DELETE) | Delete task | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/overdue | Overdue tasks | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/escalated | Escalated tasks | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/unassigned | Unassigned tasks | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/subtasks | Get subtasks | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/{id}/subtasks (POST) | Create subtask | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/subtasks/{id} | Get/Update subtask | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/subtasks/{id}/progress | Subtask progress | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/subtasks/{id}/status | Subtask status | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/subtasks/{id}/assign | Assign subtask | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Tasks | Work Management | Fully Integrated | tasks/subtasks/{id} (DELETE) | Delete subtask | N/A | 100% | Complete task management | Basic UI compelted, needs modern ui design implementations
Roles | Access Control | Fully Integrated | roles | Role list | N/A | 100% | Full role CRUD with permissions | Basic UI compelted, needs modern ui design implementations
Roles | Access Control | Fully Integrated | roles (POST) | Create role | N/A | 100% | Full role CRUD with permissions | Basic UI compelted, needs modern ui design implementations
Roles | Access Control | Fully Integrated | roles/{id} (PUT) | Update role | N/A | 100% | Full role CRUD with permissions | Basic UI compelted, needs modern ui design implementations
Roles | Access Control | Fully Integrated | roles/{id} (DELETE) | Delete role | N/A | 100% | Full role CRUD with permissions | Basic UI compelted, needs modern ui design implementations
Roles | Access Control | Fully Integrated | roles/permissions | Get permissions | N/A | 100% | Full role CRUD with permissions | Basic UI compelted, needs modern ui design implementations
Permissions | Access Control | Fully Integrated | roles/permissions | Permission list | N/A | 100% | Full permission management | Basic UI compelted, needs modern ui design implementations
Permissions | Access Control | Fully Integrated | roles/permissions (POST) | Create permission | N/A | 100% | Full permission management | Basic UI compelted, needs modern ui design implementations
Permissions | Access Control | Fully Integrated | roles/permissions/{id} (PUT) | Update permission | N/A | 100% | Full permission management | Basic UI compelted, needs modern ui design implementations
Permissions | Access Control | Fully Integrated | roles/permissions/{id} (DELETE) | Delete permission | N/A | 100% | Full permission management | Basic UI compelted, needs modern ui design implementations
Profiles | Profiles | Fully Integrated | profiles/{userId} | Get profile | N/A | 100% | Profile view and update | Basic UI compelted, needs modern ui design implementations
Profiles | Profiles | Fully Integrated | profiles/{userId} (PUT) | Update profile | N/A | 100% | Profile view and update | Basic UI compelted, needs modern ui design implementations
Organizations | Organizations | Fully Integrated | organizations | Organization list | N/A | 100% | Full organization CRUD | Basic UI compelted, needs modern ui design implementations
Organizations | Organizations | Fully Integrated | organizations/{id} | Organization details | N/A | 100% | Full organization CRUD | Basic UI compelted, needs modern ui design implementations
Organizations | Organizations | Fully Integrated | organizations (POST) | Create organization | N/A | 100% | Full organization CRUD | Basic UI compelted, needs modern ui design implementations
Organizations | Organizations | Fully Integrated | organizations/{id} (PUT) | Update organization | N/A | 100% | Full organization CRUD | Basic UI compelted, needs modern ui design implementations
Organizations | Organizations | Fully Integrated | organizations/{id}/departments/{departmentId} (PUT) | Assign department | N/A | 100% | Full organization CRUD | Basic UI compelted, needs modern ui design implementations
Organizations | Organizations | Fully Integrated | organizations/{id}/departments/{departmentId} (DELETE) | Remove department | N/A | 100% | Full organization CRUD | Basic UI compelted, needs modern ui design implementations
Organizations | Organizations | Fully Integrated | organizations/{id} (DELETE) | Delete organization | N/A | 100% | Full organization CRUD | Basic UI compelted, needs modern ui design implementations
Organization Structure | Organizations | Partially Integrated | organizations | Read-only view | Add/edit organizations not in UI | 50% | View only - needs add/edit functionality | Basic UI compelted, needs modern ui design implementations
Skills | Skills | Fully Integrated | skills | Skill list | N/A | 100% | Full skill CRUD (SuperAdmin) | Basic UI compelted, needs modern ui design implementations
Skills | Skills | Fully Integrated | skills (POST) | Create skill | N/A | 100% | Full skill CRUD (SuperAdmin) | Basic UI compelted, needs modern ui design implementations
Skills | Skills | Fully Integrated | skills/{id} (PUT) | Update skill | N/A | 100% | Full skill CRUD (SuperAdmin) | Basic UI compelted, needs modern ui design implementations
Skills | Skills | Fully Integrated | skills/{id} (DELETE) | Delete skill | N/A | 100% | Full skill CRUD (SuperAdmin) | Basic UI compelted, needs modern ui design implementations
Knowledge | Knowledge | Fully Integrated | knowledge/articles | Articles list | N/A | 100% | Knowledge base fully integrated | Basic UI compelted, needs modern ui design implementations
Knowledge | Knowledge | Fully Integrated | knowledge/articles/{id} | Article details | N/A | 100% | Knowledge base fully integrated | Basic UI compelted, needs modern ui design implementations
Knowledge | Knowledge | Fully Integrated | knowledge/articles (POST) | Create article | N/A | 100% | Knowledge base fully integrated | Basic UI compelted, needs modern ui design implementations
Knowledge | Knowledge | Fully Integrated | knowledge/articles/{id} (PUT) | Update article | N/A | 100% | Knowledge base fully integrated | Basic UI compelted, needs modern ui design implementations
Knowledge | Knowledge | Fully Integrated | knowledge/articles/{id} (DELETE) | Delete article | N/A | 100% | Knowledge base fully integrated | Basic UI compelted, needs modern ui design implementations
Knowledge | Knowledge | Fully Integrated | knowledge/lessons | Lessons learned list | N/A | 100% | Knowledge base fully integrated | Basic UI compelted, needs modern ui design implementations
Knowledge | Knowledge | Fully Integrated | knowledge/lessons (POST) | Create lesson | N/A | 100% | Knowledge base fully integrated | Basic UI compelted, needs modern ui design implementations
Knowledge | Knowledge | Fully Integrated | knowledge/lessons/{id} (PUT) | Update lesson | N/A | 100% | Knowledge base fully integrated | Basic UI compelted, needs modern ui design implementations
Knowledge | Knowledge | Fully Integrated | knowledge/lessons/{id} (DELETE) | Delete lesson | N/A | 100% | Knowledge base fully integrated | Basic UI compelted, needs modern ui design implementations
Activity Logs | Activity Logs | Fully Integrated | activitylogs | My activity logs | N/A | 100% | Activity tracking complete | Basic UI compelted, needs modern ui design implementations
Activity Logs | Activity Logs | Fully Integrated | activitylogs/user/{userId} | User logs (Admin) | N/A | 100% | Activity tracking complete | Basic UI compelted, needs modern ui design implementations
Activity Logs | Activity Logs | Fully Integrated | activitylogs (POST) | Create log | N/A | 100% | Activity tracking complete | Basic UI compelted, needs modern ui design implementations
Users | Users | Fully Integrated | users | User list | N/A | 80% | User management complete | Basic UI compelted, needs modern ui design implementations
Users | Users | Fully Integrated | users/me | Current user | N/A | 80% | User management complete | Basic UI compelted, needs modern ui design implementations
Users | Users | Fully Integrated | users/available | Available users | N/A | 80% | User management complete | Basic UI compelted, needs modern ui design implementations
Users | Users | Fully Integrated | users/workload | Workload report | N/A | 80% | User management complete | Basic UI compelted, needs modern ui design implementations
Users | Users | Fully Integrated | users/register (POST) | Register user | N/A | 80% | User management complete | Basic UI compelted, needs modern ui design implementations
Users | Users | Fully Integrated | users/{id}/availability (PATCH) | Update availability | N/A | 80% | User management complete | Basic UI compelted, needs modern ui design implementations
Users | Users | Fully Integrated | users/{id}/skills (POST) | Add user skill | N/A | 80% | User management complete | Basic UI compelted, needs modern ui design implementations
Users | Users | Fully Integrated | users/{id}/deactivate (PATCH) | Deactivate user | N/A | 80% | User management complete | Basic UI compelted, needs modern ui design implementations
Users | Users | Partially Available | users/{id}/skills/{skillId} (PUT) | Update skill | API exists but not in main UI | 80% | Missing user skill update | Basic UI compelted, needs modern ui design implementations
Users | Users | Partially Available | users/{id}/skills/{skillId} (DELETE) | Remove skill | API exists but not in main UI | 80% | Missing user skill removal | Basic UI compelted, needs modern ui design implementations
Departments | Departments | Fully Integrated | departments | Department list | N/A | 100% | Department CRUD complete | Basic UI compelted, needs modern ui design implementations
Departments | Departments | Fully Integrated | departments/{id} | Department details | N/A | 100% | Department CRUD complete | Basic UI compelted, needs modern ui design implementations
Departments | Departments | Fully Integrated | departments (POST) | Create department | N/A | 100% | Department CRUD complete | Basic UI compelted, needs modern ui design implementations
Departments | Departments | Fully Integrated | departments/{id} (PUT) | Update department | N/A | 100% | Department CRUD complete | Basic UI compelted, needs modern ui design implementations
Departments | Departments | Fully Integrated | departments/{id} (DELETE) | Delete department | N/A | 100% | Department CRUD complete | Basic UI compelted, needs modern ui design implementations
Departments | Departments | Fully Integrated | departments/{id}/dashboard | Department dashboard | N/A | 100% | Department CRUD complete | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications | User notifications | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/unread-count | Unread count | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/{id}/read (PATCH) | Mark read | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/read-all (PATCH) | Mark all read | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/{id} (DELETE) | Delete notification | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/broadcast (POST) | Broadcast notification | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/templates | Templates list | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/templates (POST) | Create template | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/templates/{id} (PUT) | Update template | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/templates/{id} (DELETE) | Delete template | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/rules | Alert rules list | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/rules (POST) | Create rule | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/rules/{id} (PUT) | Update rule | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
Notifications | Notifications | Fully Integrated | notifications/rules/{id} (DELETE) | Delete rule | N/A | 100% | Full notification system | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/providers | AI providers | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/providers/{provider}/models | Model search | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/providers/{provider}/test | Test provider | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/chat | AI chat | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/burnout-risk | Burnout risk analysis | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/insights/{projectId} | Project insights | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/project-health/{projectId} | Project health | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/optimize-resources/{projectId} | Resource optimization | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/predict-delay/{taskId} | Task delay prediction | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/recommend-assignee/{taskId} | Assignee recommendation | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/recommendations/{taskId} (POST) | Generate recommendation | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/recommendations/{taskId}/history | Recommendation history | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/recommendations/{recommendationId}/accept (POST) | Accept recommendation | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/recommendations/{recommendationId}/reject (POST) | Reject recommendation | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/recommendations/{recommendationId}/explanation | Recommendation explanation | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/tasks/{taskId}/analysis | Task analysis | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/predictions/{taskId} (POST) | Generate prediction | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/predictions/{taskId}/history | Prediction history | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/projects/{projectId}/predictions (POST) | Project predictions | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/prediction-results | Prediction results | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/models | AI models list | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/models/{modelId} | Model details | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/models (POST) | Create model | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/models/{modelId} (PUT) | Update model | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/models/{modelId} (DELETE) | Delete model | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/training-data | Training data | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/training-data (POST) | Add training data | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/performance | Model performance | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/settings | AI settings | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/settings (POST) | Save AI settings | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
AI | AI | Fully Integrated | ai/train (POST) | Trigger training | N/A | 100% | Comprehensive AI integration | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Fully Integrated | reports/stored | Stored reports | N/A | 100% | Stored reports complete | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Fully Integrated | reports/stored/{id} | Report details | N/A | 100% | Stored reports complete | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Fully Integrated | reports/stored (POST) | Create report | N/A | 100% | Stored reports complete | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Fully Integrated | reports/stored/{id} (PUT) | Update report | N/A | 100% | Stored reports complete | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Fully Integrated | reports/stored/{id} (DELETE) | Delete report | N/A | 100% | Stored reports complete | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Fully Integrated | reports/stored/{id}/download | Download report | N/A | 100% | Stored reports complete | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Fully Integrated | reports/schedules | Report schedules | N/A | 100% | Stored reports complete | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Fully Integrated | reports/schedules (POST) | Create schedule | N/A | 100% | Stored reports complete | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Fully Integrated | reports/schedules/{id} (PUT) | Update schedule | N/A | 100% | Stored reports complete | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Fully Integrated | reports/schedules/{id} (DELETE) | Delete schedule | N/A | 100% | Stored reports complete | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Not in UI | reports/project-status/{projectId} | Project status report | API exists not in UI | 100% | On-demand generation not exposed | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Not in UI | reports/task-completion | Task completion report | API exists not in UI | 100% | On-demand generation not exposed | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Not in UI | reports/department-workload | Department workload | API exists not in UI | 100% | On-demand generation not exposed | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Not in UI | reports/budget-variance/{projectId} | Budget variance | API exists not in UI | 100% | On-demand generation not exposed | Basic UI compelted, needs modern ui design implementations
Reports | Reports | Not in UI | reports/delay-analysis | Delay analysis | API exists not in UI | 100% | On-demand generation not exposed | Basic UI compelted, needs modern ui design implementations
Settings | Settings | Partially Integrated | users/me | Profile view | Password change not in settings | 50% | Basic settings - needs more options | Basic UI compelted, needs modern ui design implementations
Settings | Settings | Partially Integrated | profiles/{userId} | Profile update | Notification preferences not in settings | 50% | Basic settings - needs more options | Basic UI compelted, needs modern ui design implementations

## Updated_Status_Tracking
Module | Feature/Page | Backend Status | API Integration | UI Status | Testing Status | Refactoring Status | Remarks | Overall Completion %
Authentication | Login Page | Completed | 95% Integrated | 90% Complete - Fine tuning and alignment with updated UI standards in progress | Not Started | Not Started | Core authentication functional. UI polish and UX refinements pending. | 90%
Dashboard | Dashboard | Completed | 85% Integrated | 90% Complete - Dashboard UI mostly complete, requires fine tuning and updated design standard adjustments | Not Started | Not Started | Widgets and metrics operational. Final responsive and visual refinement pending. | 88%
Projects | Projects Page | Completed | 80% Integrated | 90% Complete - Core UI implemented with ongoing enhancement toward updated UI standards | Not Started | Not Started | CRUD operations mostly connected. AI sections and UI optimization pending. | 85%
Projects | Project Structure | Completed | 75% Integrated | 90% Complete - Basic structure and layouts complete, fine tuning in progress | Not Started | Not Started | Navigation and component hierarchy established. Requires cleanup and standardization. | 82%
Tasks | Tasks Management | In Progress | 70% Integrated | Basic UI Complete - UI improvement to updated standards in progress | Not Started | Not Started | Task workflows partially connected. Delay prediction and advanced controls pending. | 72%
Users | Users Management | In Progress | 65% Integrated | Basic UI Complete - UI modernization and refinement ongoing | Not Started | Not Started | User metrics and management screens partially integrated. | 68%
Departments | Departments Page | In Progress | 60% Integrated | Basic UI Complete - Updated UI enhancements in progress | Not Started | Not Started | Department dashboards and analytics require completion. | 63%
Notifications | Notifications Module | In Progress | 55% Integrated | Basic UI Complete - Notification experience improvements pending | Not Started | Not Started | Read/unread and broadcast partially functional. | 58%
AI | AI Insights & Assistant | In Progress | 50% Integrated | Basic UI Complete - AI workflow UI refinement ongoing | Not Started | Not Started | AI endpoints available but frontend integration incomplete. | 55%
Reports | Reports & Exports | In Progress | 45% Integrated | Basic UI Complete - Requires redesign alignment and interaction improvements | Not Started | Not Started | Export and filtering logic partially connected. | 50%
Milestones | Milestones Management | In Progress | 50% Integrated | Basic UI Complete - Visual and workflow improvements ongoing | Not Started | Not Started | Milestone tracking operational at basic level. | 52%
Settings | Settings & Configuration | Not Started | 0% Integrated | Not Started | Not Started | Not Started | Planned for future implementation. | 5%
Testing | Unit & Integration Testing | Not Started | 0% Integrated | Not Applicable | Not Started | Not Started | Comprehensive testing strategy still pending and required in future phases. | 0%
Refactoring | Codebase Refactoring & Optimization | Not Started | 0% Integrated | Not Applicable | Not Started | Not Started | Architecture cleanup, optimization, and standardization required in future. | 0%
Documentation | Technical & User Documentation | In Progress | 20% Integrated | Basic UI Complete | Not Started | Not Started | API and architecture documentation partially available. | 25%